## Sheet1
Identification |  | Quantification |  |  | Response
Risk Identification | Impact | Probability (1 -10) | Estimated Impact (1-10) | Risk Ranking (Prob. X Impact) | Mitigation plan | Requires Attention
Have not signed contract or confirm April slot date | Risk of extended time needed to implement order entry. May cause Sample Hospital to miss cutoff for early stimulus payment | 7 | 8 | 56 | work toward completing contract and getting commitment on start dates. If not rework schedule and delay project | Y
Aggressive timeframe for implementing CPOE | Target timeframe for CPOE go live may not be realistic based upon industry results. | 7 | 8 | 56 | Develop project initiation workplan to prepare. Work with CPOE Vendor to develop a realistic schedule based upon all pertinent factors. Communicate to leadership what realistic timeframe is. | Y
Order Set development needs high physician involvement | Orders sets may not be acceptable if physicians are not engaged. This process has taken 6 - 12 months at comparable hospitals | 7 | 8 | 56 | Create physician team to work with an order set group | Y
Physician champion not secured | Delays and risk of lack of buy in from limited physician input. Increased chance for lack of physician compliance | 7 | 5 | 35 | Aggresively pursue securing physician champion. | Y
CPOE Vendor has had limited live implementations of CPOE software. | Limited experiences to gauge best practices and effort needed to implement CPOE | 5 | 6 | 30 | Close tracking of project plan and schedule. Diligence in up front planning | N
System changes may be limited during roll out of project due to system upgrade requirements | Will note the to make certain changes to refine the system after go live. Shortens project timeframe to go live with order entry | 5 | 5 | 25 | develop plan to stabilize COE system prior to 10.1 project. Fully understand what the limitations will be | N
Simultaneous work on CPOE and Emergency Charting (EDIS) | Potential for inadequate resources from competing plans. Additional project complexity | 5 | 5 | 25 | Contract ED project. Identify overlap of projects in master project plan | Y
Physician adoption may not meet “meaningful use” | Sample Hospital at risk for not receiving maximum stimulus incentive from ARRA | 3 | 6 | 18 | Aggressively communicate with physicians. Build physician teams to help build order process | Y
Large number of prerequisite tasks - linked with implementing the CPOE system | Adds to complexity of plan. Any delays will delay order entry | 3 | 6 | 18 | Closely monitor prerequisite tasks in order to keep project on schedule | N
ARRA requirement for physician ambulatory EMR | Resources may get pulled to assist with physician ambulatory efforts. | 3 | 5 | 15 | Additional initiatives will need to secure additional resources outside of the existing pool | N
Inadequate training | Ineffective use of the system | 1 | 7 | 7 | Develop comprehensive training plan | N
Inadequate staffing to implement or support system | Delays in implementation. Lack of support for operational system. | 1 | 7 | 7 | Obtain necessary staff to implement and support the system - hospital and IT staff | N
Non-managed scope changes | Delays in project. Additional costs. | 1 | 7 | 7 | Adhere to scope management plan | N
Lack of participation by key stakeholders as defined in the project plan | Support for project not provided. Tasks not assigned or completed. | 1 | 6 | 6 | Obtain key stakeholder sign off for roles and responsibilities | N
Roles & Responsibilities not agreed to or clearly understood | Accountability not assigned to deliverables | 1 | 6 | 6 | Develop and obtain approval for RAM | N
Scope of effort needed to complete project underestimated | Delays in project | 1 | 6 | 6 | Document project scope and obtain approval | N
Lack of updated project tracking | Potential rework and delays. Inability to identify and address issues. | 1 | 6 | 6 | Regular updates of project work plan, Regular status reporting | N
Date of Risk Review | 2010-03-08
Risk Assessment Notes | The items listed here are general project risks at project start-up. As the project progresses, the probability will either increase or the risk will be eliminated and removed.